SVdP Voucher System Cutover

Technical transition overview for merging databases, promoting the new voucher site, and retiring the pilot route

Primary domain: svdpfortwayne.org

Pilot/current voucher domain: voucher.svdpfortwayne.org

Platform root: /opt/wordpress-platform

Cutover target: Route production traffic to the new voucher WordPress container after final data reconciliation

Core principle The final merge is not a whole-database import. The old production site and the new voucher site may both accumulate writes during the pilot window, so the cutover must apply a controlled delta from legacy production into the new voucher database.

# 1. Confirm the Starting Architecture

Before cutover, confirm that the old production and new voucher systems are isolated and that Caddy is the only public routing point.

The public production domain currently routes through Caddy to the old production WordPress container.

The voucher subdomain routes through Caddy to the new voucher WordPress container.

The new voucher WordPress container uses its own MariaDB container and not the old production database.

The new voucher stack has separate Docker volumes for WordPress files and database data.

The new voucher wp-content path is separate from production wp-content.

The critical invariant is that the new voucher site is the future production system, while the old production site is only a source of final legacy changes.

# 2. Establish the Pilot Baseline

At the moment the voucher site is seeded from production, preserve a baseline snapshot. This baseline is what makes the final database reconciliation possible.

Preserve the old production database dump at the clone moment.

Preserve the old production wp-content archive at the clone moment.

Preserve the new voucher database immediately after import.

Preserve the new voucher wp-content immediately after import.

Record timestamps, file names, source containers, target containers, and checksums.

Later, the final merge compares the old production database at cutover against this baseline to determine what changed while the voucher site was being piloted.

# 3. Run the Pilot With Clear Data Ownership

During the pilot period, both systems are live. The organization needs explicit ownership rules so the final merge is deterministic.

Pilot Conferences use the new voucher site.

Non-pilot Conferences continue using the old production site.

Cashiers may need access to both cashier stations.

A voucher or request should be edited or redeemed only in the system where it was created or assigned.

Exceptions should be logged and reconciled deliberately.

Expected collision Because the voucher database begins as a clone, both systems can create new rows with the same numeric primary keys after the clone. The merge process must expect this and maintain an ID map.

# 4. Prepare for Final Cutover

Before the cutover window, rehearse the merge using recent copies of both databases. The rehearsal should produce a conflict report and prove that the merge rules are complete.

Identify WordPress core tables, voucher plugin tables, other plugin tables, and configuration-only tables.

Identify tables that require row-level delta merging rather than replacement.

Check for primary-key collisions and foreign-key or implicit relationship dependencies.

Compare upload paths and content hashes for file collisions.

Reconcile voucher counts, accounting totals, status totals, and Conference totals.

Resolve conflicts requiring human judgment before the production window.

# 5. Freeze Writes

At the start of final cutover, freeze writes on both systems. The final database state must stop moving before the last delta is captured.

Freeze public voucher requests.

Freeze cashier actions and partner-facing voucher activity.

Freeze voucher admin changes, configuration edits, user changes, and media changes that could affect the merged result.

Use a maintenance response, temporary access restriction, or application-level read-only mode.

Keep the freeze in place until post-cutover acceptance is complete.

# 6. Take Final Backups

After the freeze, take fresh backups of both systems and validate them before making any irreversible changes.

Back up old production database and wp-content.

Back up new voucher database and wp-content.

Back up Docker Compose, environment configuration, and the Caddyfile.

Record the freeze timestamp and the backup timestamp.

Validate backup readability and checksums before proceeding.

If backup validation fails, stop the cutover and fix the backup process first.

# 7. Generate the Legacy Delta

Compare the final old production database against the pilot baseline. For each relevant table, classify rows according to how they changed since the baseline.

Rows unchanged since baseline require no action.

Rows inserted in old production after baseline must be imported into the new voucher database.

Rows updated in old production after baseline must be applied only if the new voucher database did not independently change the same logical row.

Rows deleted or missing from old production should not cause hard deletes in the new voucher database without review.

Do not rely only on timestamps unless every relevant table has trustworthy update timestamps. Primary-key comparison plus normalized row hashing is safer.

# 8. Apply the Delta Into the New Voucher Database

Apply legacy-side changes into the new voucher database using deterministic rules and a persistent ID map.

## Rows that existed at baseline

If old production changed the row and the new voucher database did not, update the new voucher row.

If both systems changed the same row, record a conflict for manual resolution.

If the old production row disappeared, do not hard-delete it from the new voucher database without review.

## Rows inserted after baseline

Insert legacy-only rows into the new voucher database.

If the numeric ID is already used by a different new voucher row, assign a new ID and record the mapping.

Update child rows, dependent rows, and implicit references to follow the ID map.

## Voucher-specific relationships

Preserve relationships across vouchers, request groups, voucher items, fulfillment entries, accounting rows, audit rows, photos, receipts, invoices, and related metadata.

Preserve old-only legacy tables read-only if they matter for history, reporting, or audit.

# 9. Merge Uploads and Generated Files

Merge production uploads into the new voucher site's uploads directory using relative paths and content hashes.

Copy files that exist only in old production.

Treat files with the same path and same hash as already merged.

Stop and resolve any same-path, different-content collision manually.

Pay particular attention to media library files, voucher PDFs, receipts, furniture photos, accounting exports, and generated documents.

After merging, ensure ownership and permissions match the WordPress container's runtime user.

# 10. Update WordPress Runtime URLs

Once the new voucher database is the final production database, update its WordPress URL settings.

Set home to https://svdpfortwayne.org.

Set siteurl to https://svdpfortwayne.org.

Use a serialization-safe WordPress search-replace for content, options, and post meta that may contain the pilot hostname.

Check for hardcoded pilot, staging, local development, or old server URLs.

Serialization caveat Do not use naive SQL replacement across serialized WordPress options or post meta. Use a WordPress-aware search-replace tool when replacing the pilot hostname in stored content.

# 11. Promote the New Container at Caddy

If DNS already points to this server, Caddy is the public cutover point.

Change the production domain route so it proxies to the new voucher WordPress container instead of the old production WordPress container.

Change the voucher subdomain from serving the pilot site to redirecting to the production domain.

Keep the www hostname redirecting to the apex production domain.

Remove the noindex header from the final production domain if it was inherited from the pilot route.

Validate the Caddyfile before reloading Caddy.

# 12. Update DNS If Needed

DNS may not need to change if the production domain already resolves to this server. If it does need to change, keep the DNS step coordinated with the Caddy promotion.

Point the apex domain to the server.

Point www to the apex domain or the same target.

Point the voucher subdomain to the same target if it remains as a redirect.

Lower TTLs ahead of the maintenance window where possible.

If Cloudflare is involved, confirm proxy mode, TLS mode, and cache behavior.

Verify public resolution before accepting the cutover.

# 13. Run Acceptance Checks

After routing changes, validate that the new production site is functional and that the merged data is complete.

Check homepage, login, admin dashboard, voucher request form, cashier station, and REST endpoints.

Exercise duplicate detection, voucher creation, voucher redemption, Conference filtering, partner workflows, and accounting/report views.

Confirm generated documents and media render correctly.

Confirm XML-RPC remains blocked.

Confirm the pilot subdomain redirects and no longer exposes the pilot interface.

Compare final counts for vouchers by status, type, and Conference; redemptions; audit records; accounting totals; request groups; fulfillment rows; and uploaded/generated files.

# 14. Keep the Old Production Stack Intact

Do not remove the old production containers, database volume, or wp-content immediately after cutover.

Remove public routing to the old production WordPress container.

Keep the old stack available for reference or rollback.

Prevent new voucher writes in the old system.

Preserve final backups, merge receipts, and conflict reports.

Retire old containers and volumes only after the stabilization period and explicit approval.

# 15. Rollback Considerations

Rollback depends on how far the cutover progressed.

If only Caddy routing changed, rollback can usually route the production domain back to the old production WordPress container.

If the new database was modified by final merge, rollback is a data decision, not only a routing decision.

If users created post-cutover data in the new production system, freeze writes again before rollback decisions.

Choose whether to fix forward, restore the new site from pre-merge backup, or route back to old production and preserve post-cutover writes for later reconciliation.

# 16. Post-Cutover Monitoring

For the first several days, monitor application health and data integrity closely.

Watch WordPress, PHP, Caddy, and database logs.

Watch failed REST requests, failed voucher submissions, and cashier station behavior.

Check accounting/report discrepancies, missing uploads, unexpected redirects, session issues, DNS issues, and certificate issues.

Run daily reconciliation reports until the organization accepts the new system as the single source of truth.